# SOP Steward Integration - Luna Digital Marketing Workflow Redesign

\*\*Document ID\*\*: LUNA\_SOP\_STEWARD\_FRAMEWORK

\*\*Created\*\*: 2025-09-12

\*\*Status\*\*: Implementation Phase

## Table of Contents

1. [SOP Steward Integration Overview](#sop-steward-integration-overview)

2. [Content Audit Against Current SOPs](#content-audit-against-current-sops)

3. [Critical Issues Identified](#critical-issues-identified)

4. [SOP-Compliant Content Framework](#sop-compliant-content-framework)

5. [Implementation Phases](#implementation-phases)

6. [Quality Assurance Protocol](#quality-assurance-protocol)

## SOP Steward Integration Overview

### \*\*CRITICAL REQUIREMENT\*\*: SOP Steward as Mandatory First Step

**NEW WORKFLOW PROTOCOL:**

* \*\*Phase 0\*\*: SOP Steward review BEFORE any content creation begins
* \*\*Compliance Check\*\*: Verify against existing brand and content standards
* \*\*Gap Analysis\*\*: Identify deviations from established SOPs
* \*\*Framework Application\*\*: Apply SOP-compliant structure to all content
* \*\*Copywriter Briefing\*\*: Ensure SOP knowledge before content creation

### SOP Steward Role Definition

**Primary Responsibilities:**

1. \*\*Pre-Content Review\*\*: Audit brief against established SOPs

2. \*\*Compliance Verification\*\*: British English, Australian context, professional standards

3. \*\*Brand Consistency\*\*: Ensure alignment with Luna Digital brand guidelines

4. \*\*Quality Standards\*\*: Verify Answer First sections, character counts, source citations

5. \*\*Regulatory Compliance\*\*: AHPRA guidelines, professional services standards

## Content Audit Against Current SOPs

### \*\*MAJOR COMPLIANCE GAPS IDENTIFIED:\*\*

#### 1. Director Information Inconsistency

* \*\*Current Issue\*\*: Multiple references to "Sarah Matthews" instead of "Natasha Chandra"
* \*\*Files Affected\*\*: Meet Our Director page, About Us sections, author attributions
* \*\*Compliance Risk\*\*: Brand credibility and factual accuracy concerns
* \*\*SOP Violation\*\*: Factual accuracy and brand consistency requirements

#### 2. Unsubstantiated Claims Throughout Content

* \*\*Issue\*\*: Response time guarantees without supporting evidence
* \*\*Examples\*\*: "24-hour response guarantee", "immediate consultation availability"
* \*\*SOP Violation\*\*: All claims must have credible source citations
* \*\*Risk Level\*\*: High - potential false advertising implications

#### 3. Missing Answer First Sections

* \*\*Current State\*\*: Executive summaries instead of Answer First structure
* \*\*SOP Requirement\*\*: All pages must begin with direct answer to user query
* \*\*Compliance Gap\*\*: 100% of pages lack proper Answer First implementation
* \*\*Impact\*\*: SEO performance and user experience degradation

#### 4. Target Market Too Narrow

* \*\*Issue\*\*: Exclusive focus on "professional services only"
* \*\*Market Reality\*\*: Luna Digital serves broader business community
* \*\*SOP Requirement\*\*: Accurate representation of service capabilities
* \*\*Business Impact\*\*: Limiting lead generation and market positioning

#### 5. Character Count Assessment Missing

* \*\*Gap\*\*: No systematic character count verification in quality checks
* \*\*SOP Standard\*\*: Meta descriptions must be 155 characters, titles 60 characters
* \*\*Current Risk\*\*: SEO performance limitations and search result truncation

## Critical Issues Identified

### \*\*IMMEDIATE ACTION REQUIRED:\*\*

#### 1. Brand Identity Crisis

```yaml

Current\_State: "Sarah Matthews, Professional Services Marketing Specialist"

Required\_State: "Natasha Chandra, Founder & Managing Director"

Impact: Complete brand messaging inconsistency

Priority: CRITICAL - Must fix before any content goes live

```

#### 2. False Claims Liability

```yaml

Current\_Risk: "Response time guarantees without evidence"

Legal\_Exposure: "Potential false advertising violations"

Action\_Required: "Remove all unsubstantiated performance claims"

Priority: HIGH - Legal compliance issue

```

#### 3. SEO Structure Non-Compliance

```yaml

Missing\_Elements: "Answer First sections on all pages"

Performance\_Impact: "Reduced search visibility and user engagement"

Compliance\_Gap: "2025 content standards not implemented"

Priority: HIGH - SEO performance degradation

```

#### 4. Market Positioning Limitation

```yaml

Current\_Limitation: "Professional services only positioning"

Business\_Reality: "Broader service capabilities available"

Revenue\_Impact: "Reduced lead generation potential"

Priority: MEDIUM - Growth opportunity limitation

```

## SOP-Compliant Content Framework

### \*\*MANDATORY FRAMEWORK ELEMENTS:\*\*

#### 1. Answer First Structure (Required on ALL Pages)

```markdown

# Page Title

## Answer First Section

[Direct answer to primary user query in first 150 words]

## Traditional Content Structure Follows

[Rest of page content with proper headings and structure]

```

#### 2. Director Information Standard

**Consistent Throughout All Content:**

* \*\*Name\*\*: Natasha Chandra
* \*\*Title\*\*: Founder & Managing Director
* \*\*Credentials\*\*: [To be verified and documented]
* \*\*Bio\*\*: Updated professional background and expertise

#### 3. Claims Verification Protocol

**All Claims Must Include:**

```markdown

**Statistic or Performance Claim**

\*\*Source:\*\* [Organisation Name - Report Title](URL) - Date

```

#### 4. Character Count Compliance

* \*\*Page Titles\*\*: Maximum 60 characters
* \*\*Meta Descriptions\*\*: Maximum 155 characters
* \*\*H1 Headers\*\*: Maximum 70 characters for optimal display
* \*\*Navigation Labels\*\*: Maximum 20 characters

#### 5. British English Compliance Verification

**Mandatory Spellings:**

* optimise (not optimize)
* realise (not realize)
* colour (not color)
* centre (not center)
* organisation (not organization)

#### 6. Target Market Broadening Framework

**New Positioning:**

* \*\*Primary Focus\*\*: Professional services (maintain strength)
* \*\*Extended Services\*\*: All business types requiring marketing expertise
* \*\*Messaging\*\*: "Specialising in professional services, serving all businesses"

## Implementation Phases

### \*\*Phase 1: Immediate Corrections (Week 1)\*\*

* [ ] \*\*Director Name Updates\*\*: Change all "Sarah Matthews" to "Natasha Chandra"
* [ ] \*\*Unsubstantiated Claims Removal\*\*: Remove response time guarantees and unverified statistics
* [ ] \*\*Answer First Implementation\*\*: Convert executive summaries to Answer First structure
* [ ] \*\*Character Count Audit\*\*: Verify and correct all meta elements

### \*\*Phase 2: Content Enhancement (Week 2)\*\*

* [ ] \*\*Target Market Broadening\*\*: Expand messaging beyond professional services only
* [ ] \*\*Source Citation Addition\*\*: Add credible sources for all retained statistics
* [ ] \*\*British English Verification\*\*: Complete spelling and terminology audit
* [ ] \*\*Navigation Structure Updates\*\*: Fix "Areas We Serve" section headings

### \*\*Phase 3: AI Optimisation Integration (Week 3)\*\*

* [ ] \*\*AI Readiness Review\*\*: Complete technical optimisation for AI systems
* [ ] \*\*Structured Data Implementation\*\*: Add schema markup recommendations
* [ ] \*\*Voice Search Compatibility\*\*: Optimise content for voice queries
* [ ] \*\*Content Consolidation\*\*: Numbered page structure in single folder

### \*\*Phase 4: Quality Assurance & Go-Live (Week 4)\*\*

* [ ] \*\*Final SOP Compliance Check\*\*: Comprehensive audit against all standards
* [ ] \*\*Feedback Loop Testing\*\*: Verify enhanced feedback system operation
* [ ] \*\*Sitemap Verification\*\*: Confirm all pages complete and compliant
* [ ] \*\*Implementation Timeline\*\*: Prepare website update schedule

## Quality Assurance Protocol

### \*\*SOP Steward Quality Gates:\*\*

#### Gate 1: Content Brief Review

* [ ] Answer First structure planned
* [ ] Director information correct (Natasha Chandra)
* [ ] Target market appropriately broad
* [ ] Character count specifications included
* [ ] Source citation requirements identified

#### Gate 2: Draft Content Review

* [ ] Answer First section implemented correctly
* [ ] All claims supported by credible sources
* [ ] British English compliance verified
* [ ] Character counts within limits
* [ ] Brand messaging consistent

#### Gate 3: Pre-Publication Review

* [ ] Final SOP compliance verification
* [ ] Cross-reference accuracy check
* [ ] Link functionality verification
* [ ] Mobile compatibility confirmed
* [ ] SEO elements optimised

### \*\*Enhanced Feedback Loop Integration:\*\*

```yaml

sop\_compliance\_check:

type: MandatoryPreCheck

agent: SOP\_Steward

threshold\_score: 9.0/10.0

requirements:

* director\_name\_correct: true
* answer\_first\_present: true
* claims\_supported: true
* character\_counts\_compliant: true
* british\_english\_verified: true

```

### \*\*Success Metrics:\*\*

* \*\*Brand Consistency\*\*: 100% director name accuracy
* \*\*Claims Compliance\*\*: All statistics have credible sources
* \*\*SEO Structure\*\*: Answer First on all pages
* \*\*Character Compliance\*\*: Meta elements within limits
* \*\*Market Positioning\*\*: Broader appeal while maintaining professional services strength

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

\*\*Next Action\*\*: Begin immediate implementation of director name corrections and unsubstantiated claims removal across all Luna Digital content files.

\*\*Quality Assurance\*\*: SOP Steward verification at each phase gate before proceeding to next implementation phase.